## Ostrevane - Design and accessib
Ostrevane - Design and accessibility
In progress
Name | Person | Status | Timeline | Due date | Time Tracking | Jira link | Item ID
Beta design sign-off | Freya Castell | Stuck | 2026-09-22 - 2026-09-28 | 2026-09-28 | 6:00:00 | KEL-3 | 7182640011
Accessibility audit: wallet | Marisol Vega | Working on it | 2026-09-26 - 2026-10-07 | 2026-10-07 | 18:00:00 | KEL-4 | 7182640028
| Subitems | Owner | Status | Date | Item ID
| Screen reader pass | Marisol Vega | Done | 2026-09-30 | 7182640014
| Contrast pass | Marisol Vega | Working on it | 2026-10-05 | 7182640017
Payment screens final | Joss Whitlow | Working on it | 2026-09-29 - 2026-10-09 | 2026-10-09 | 9:30:00 |  | 7182640039
Illustrations: onboarding |  | Working on it | 2026-09-20 - 2026-10-04 | 2026-10-04 |  |  | 7182640050
Up next
Name | Person | Status | Timeline | Due date | Time Tracking | Jira link | Item ID
Accessibility audit: journey planner | Marisol Vega | Not started | 2026-10-08 - 2026-10-17 | 2026-10-17 |  | KEL-4 | 7182640061
App store screenshots | Joss Whitlow | Not started | 2026-10-12 - 2026-10-20 | 2026-10-20 |  | KEL-3 | 7182640072
Content style guide | Marisol Vega | Not started | 2026-10-14 - 2026-10-22 | 2026-10-22 |  |  | 7182640083
Done
Name | Person | Status | Timeline | Due date | Time Tracking | Jira link | Item ID
Discovery synthesis | Freya Castell | Done | 2026-08-03 - 2026-08-17 | 2026-08-17 | 32:00:00 |  | 7182640094
Design system tokens | Joss Whitlow | Done | 2026-08-18 - 2026-09-02 | 2026-09-02 | 40:30:00 |  | 7182640105
Journey planner flows | Joss Whitlow | Done | 2026-08-28 - 2026-09-10 | 2026-09-10 | 36:00:00 | KEL-1 | 7182640116
Wallet flows | Joss Whitlow | Done | 2026-09-04 - 2026-09-17 | 2026-09-17 | 30:00:00 | KEL-2 | 7182640127